## Crew (Ready)
Username | Temporary PW | Name | Email (for login) | Phone | Wizard Role
jrogers | waterproof_it | Jordan Rogers | estimating@vanislecoatings.com | 250-883-7175 | Admin
tclark | waterproof_it | Tara Clark | ops@vanislecoatings.com | 778-688-0759 | Admin
jdares | waterproof_it | Jesse Dares | crewlead@vanislecoatings.com | 778-678-4511 | Manager
jgregoire | waterproof_it | Jonathan Gregoire | jongregoire95@gmail.com | 613-539-5322 | Crew
jthorpe | waterproof_it | Jordan Thorpe | jordanthorpe1995@outlook.com | 250-886-1599 | Crew
jmurray | waterproof_it | Joshua Murray | joshm3972@gmail.com | 250-891-5620 | Crew
lpardy | waterproof_it | Logan Pardy | loganpardy96@gmail.com | (250) 508--0353 | Crew
bwagner | waterproof_it | Bobby Wagner | bymsid@gmail.com | 250-589-3697 | Crew
rayb | waterproof_it | Ray Boudreault | rayboudreault@yahoo.ca | 250-880-2489 | Crew
ssmith | waterproof_it | Shane Smith | smith.shane.allan@gmail.com | 250-580-2553 | Crew
dscott | waterproof_it | Desmond Scott | desmondscot@gmail.com |  | Crew
jacobv | waterproof_it | Jacob V | jacob.valentin.soto@gmail.com | (250) 882-8666 | Crew
ktaylor | waterproof_it | Ken Taylor | kenadian99@gmail.com |  | Crew
dmarshall | waterproof_it | David | givertilluquiver@gmail.com |  | Crew
mhorne | waterproof_it | Manny | Emannual98@gmail.com |  | Crew

## Inventory at warehouse
Inventory | Category | Service | Vendor | Secondary Vendor | Unit (locked) | Units per | Unit Cost ($) Before July 30 | Unit Cost ($) As of August | On Hand (current quantity) - WILL BE PROVIDED BY AUGUST 11 | As of Date | Reorder At (3 remaining in inventory) | Warehouse Location | Verify Minimum Sock
Pekora Dynafex - EllisDon CBH | Caulking & Sealants | Caulking | BC Firestopping | N/A | Sausage | 12/Case | 16.6
Injection Rope - Sealboss Inject Tube | Crack Injection | Crack Injection | Cascade | N/A | roll | Per metre | 16
Xylene 19L Cleaning Solvent | Traffic Coatings | Conventional, Blindside, Traffic Coating, Caulking , CFI, XPS, Crack Injection | Cascade | N/A | unit |  |  |  | 2
Xylene 4L Cleaning Solvent | Traffic Coatings | Conventional, Blindside, Traffic Coating, Caulking , CFI, XPS, Crack Injection | Cascade | N/A | unit |  | 42.72 | 44.86
Soft Rod 3/8" Baby Backer 2100'/cs | Caulking & Sealants | Caulking | Cascade | Tremco | unit |  | 116.17
Soft Rod 5/8" Soft Type Backer Rod, 1,550'CTN | Caulking & Sealants | Caulking | Cascade | Tremco | unit |  | 144.63
Soft Rod 7/8" Soft Type Backer Rod, 850'/CTN | Caulking & Sealants | Caulking | Cascade | Tremco | unit |  | 134.6
Soft Rod 1-1/8" Soft Type Backer Rod, 500'/CTN | Caulking & Sealants | Caulking | Cascade |  | unit |  | 141
Dow CWS (Grey) | Caulking & Sealants | Caulking | Cascade | N/A | Sausage |  |  | 10.5 | 0
Dow CWS (White) | Caulking & Sealants | Caulking | Cascade | N/A | Sausage |  |  | 10.5 | 0
Seal Boss catalyst 15x ( accelerator) | Crack Injection | Crack Injection | Cascade | N/A | unit
Injection Port ZINC HD 1/2" x 3" Metal 100/bg 13-70 ZI | Crack Injection | Crack Injection | Cascade | N/A | unit |  | 2.59 | 4.25
Injection Ports 3/8" Plastic WHITE w/Grease Fitting 100/Bag ( 318 per bag ) | Crack Injection | Crack Injection | Cascade | N/A | unit |  | 0.31 | 1.59
Knife- puttyflex 1-9/16 plastic | Traffic Coatings | Caulking | Cascade | N/A | unit |  | 1.7
replacement spikes ( 32 units) | Traffic Coatings | Traffic Coating | Cascade | N/A | unit |  | 67.28
Seal Boss 6500 PART A (crack chasing) | Crack Injection | Crack Injection | Cascade | N/A | litre |  |  |  | 0.75
Seal Boss 6500 PART B (crack chasing) | Crack Injection | Crack Injection | Cascade | N/A | litre |  |  |  | 0.75
SealBoss 1570 PU Injection Grout 5 gal ( 18.9 L) | Crack Injection | Crack Injection | Cascade | N/A | unit |  | 688.92 |  | 1
SealBoss 1510 PU Injection Grout 5 gal ( 18.9 L) | Crack Injection | Crack Injection | Cascade | N/A | unit |  |  | 672.92
sealboss oakum (7 x1 ft bag) | Crack Injection | Crack Injection | Cascade | N/A | unit |  | 29.19
SealBoss R70 Pump Flush 5 gal ( 18.9l L) | Crack Injection | Crack Injection | Cascade | N/A | unit |  | 394.59 |  | 0.25
SealBoss Inject Tube Typell TUBE (per meter) | Crack Injection | Crack Injection | Cascade | N/A | unit |  |  | 16
SealBoss Inject Tube Typell SCREW | Crack Injection | Crack Injection | Cascade | N/A | unit |  |  | 4.18
SealBoss Inject Tube Typell SLEEVE | Crack Injection | Crack Injection | Cascade | N/A | unit |  |  | 8.72
Silica Sand 16 grit - 50 lb bag Vehicular (56 bg/pallet) | Traffic Coatings | Traffic Coating | Cascade | N/A | unit |  | 21.74 | 23.6 | 16
Silica Sand 20/30 50 lb bag Pedestrian (56 bg/pallet) | Traffic Coatings | Traffic Coating | Cascade | N/A | unit |  | 21.74 | 20.52 | 4
Squeegee 26" 25- 30 ml blade | Traffic Coatings | Traffic Coating | Cascade | N/A | unit |  | 35
Squeegee 26" 15-20 ml blade | Traffic Coatings | Traffic Coating | Cascade | N/A | unit |  | 35
Towels Rags White Ganzies 10 lb bag | shop | Conventional, Blindside, Traffic Coating, Caulking , Crack Injection | Cascade | N/A | unit |  | 28.45
Micro pro sleeve 14 inx15 | Traffic Coatings | Traffic Coating | Cloverdale | N/A | unit |  | 8.36
Microfibre roller sleeves 18” | Traffic Coatings | Traffic Coating | Cloverdale | N/A | unit |  | 7.15 | 7.38
Microfibre Refills ( wizz rollers) 4 “ ( 10 pack) | Traffic Coatings | Traffic Coating | Cloverdale | N/A | unit | 10 | 14.6 | 14.66
2" chip brush ( 10 pieces) | Traffic Coatings | Traffic Coating | Cloverdale | N/A | Box | 10 | 15.2 | 8.88
1" in chip brush ( 10 pieces) | Traffic Coatings | Traffic Coating | Cloverdale | N/A | Box | 10 | 11.6 | 8.88
Painters Masking Tape | Traffic Coatings | Traffic Coating | Cloverdale | N/A | unit | 4 pack |  | 20.24
Pelican Liner (4pack) | Traffic Coatings | Traffic Coating | Cloverdale | N/A | unit | 4pack | 5.66
36 MM painters mate contractors tape | Traffic Coatings | Traffic Coating | Cloverdale | N/A | unit |  | 21.9
Sherlock Pro Cage frame 14-18” | Traffic Coatings | Traffic Coating | Cloverdale | N/A | unit |  | 62.99 | 45.01
2 quart mixing cup multi ratio | Traffic Coatings | Traffic Coating | Cloverdale | N/A | unit |  | 1.7
5 quart measuring cup | Traffic Coatings | Traffic Coating | Cloverdale | N/A | unit |  | 3.5
mixing cup multi ratio 12 oz | Traffic Coatings | Traffic Coating | Cloverdale | N/A | unit |  | 0.53
mixing cup multi ratio 22 oz | Traffic Coatings | Traffic Coating | Cloverdale | N/A | unit |  | 0.71
mixing cup multi ratio 44 oz | Traffic Coatings | Traffic Coating | Cloverdale | N/A | unit |  | 1.07
4.5 L plastic white plastic pail | Traffic Coatings | Traffic Coating | Cloverdale | N/A | unit |  | 4.85
5L pail yellow | Traffic Coatings | Traffic Coating | Cloverdale | N/A | unit |  | 8.5
Barricade Tape (Red) | PPE | Conventional, Traffic Coating | Columbia Fire Safety | N/A | unit |  | 11.62
Advance care 3.5 ml nitrile gloves blue (100bx) | PPE | Conventional, Traffic Coating | Columbia Fire Safety | N/A | unit |  | 10.36
black nitrile gloves 6 ml | PPE | Conventional, Blindside, Traffic Coating, Crack Injection | Columbia Fire Safety | N/A | box | 100 | 11.96
Cotton Spray Hood | PPE | Conventional, Blindside | Columbia Fire Safety | N/A | unit | 1 | 2.84
Disposable coveralls XL w/ hood and elastic ankles | PPE | Conventional, Blindside, Traffic Coating, Crack Injection | Columbia Fire Safety | N/A | unit |  | 4.7 | 4.76
Disposable coveralls XL w/ hood and boots | PPE | Conventional, Blindside, Traffic Coating, Crack Injection | Columbia Fire Safety | N/A | unit |  |  | 5.2
Clear Goggle, Columbia | PPE | Conventional, Blindside, Traffic Coating, Crack Injection | Columbia Fire Safety | N/A | unit |  | 4.39 | 3.69
Stealth Saftey Goggles (Anti-Fog) | PPE | Conventional, Blindside, Traffic Coating, Crack Injection | Columbia Fire Safety | N/A | unit |  |  | 25.96
North Cartridge organic vapour ( gasses) | PPE | Blindside, Conventional, Traffic Coating | Columbia Fire Safety | N/A | unit |  | 24.72
North Respirator (Half Mask) Rubber | PPE | Blindside, Conventional, Traffic Coating | Columbia Fire Safety | N/A | unit | 1 | 23.16
North Filter, Particulates, P100 | PPE | Blindside, Conventional, Traffic Coating | Columbia Fire Safety | N/A | unit |  | 15.7
Layfield vapour barrier ( 14x140 =1,960 sq.ft ) | Waterproofing | Conventional | Convoy | N/A | unit |  | 608.56 |  | 0
Alsan Flashing/LM Barr Polyfleece 6inx100ft | Waterproofing | Conventional, Blindside | Convoy | N/A | roll |  | 43.8 | 55 | 2
Soprema Alsan flashing 19 L | Waterproofing | Conventional, Blindside | Convoy | N/A | unit |  | 505.95 | 572.75 | 2
Soprema Colphene BSW V (3.28' x32.8') | Waterproofing | Blindside | Convoy | N/A | unit |  | 119 | 121.95 | 0
Soprema 10-G drainmat (6*50) | Waterproofing | Blindside, Conventional | Convoy | N/A | unit |  | 189 | 208.89 | 0
Soprema Sopraseal Primer 19L | Waterproofing | Conventional | Convoy | N/A | unit |  | 182 | 218.55 | 0
Target Spec Mix ( concrete ) 36.3 kg bag | Crack Injection | Crack Injection | Convoy | N/A | unit |  | 80
Fender Washer Plated 1/4 by 1x 1/4 | Waterproofing | Conventional, Blindside | Fastner Force | N/A | unit |  | 0.1785
Screws | Waterproofing | Conventional, Blindside | Fastner Force | N/A | Box | 100/case | 38
G 13 6mm straight grease fitting | Crack Injection | Crack Injection | Greenline |  | unit |  | 0.48
G13 02 grease gun coupler standar duty narrow model | Crack Injection | Crack Injection | Greenline |  | Unit |  | 3.39
26 Gauge flashing 8 ft | Waterproofing | CFI | Ken's Roofing | N/A | unit |  | 12.38
50 amp big blade fuse ( shot blaster repair) | Consumables & Prep | Shop | Lordco | N/A | unit |  | 4
Garage bags ( contractor) | Consumables & Prep | Blindside | RONA | WhiteCap | Box |  | 21.84 |  | 1
duck tape | Traffic Coatings | Traffic Coating | RONA | N/A | unit |  | 10.06
18.9 pail yellow | Traffic Coatings | Traffic Coating | RONA | N/A | unit |  | 4.49
18.9 pail yellow LID | Traffic Coatings | Traffic Coating | RONA | N/A | unit |  | 1.43
Lepage Heavy Duty Adhesive Spray Glue | Waterproofing | Blindside | RONA | N/A | unit |  | 37.04 |  | 1
epoxy quickset- hydrolic line repair for shot blaster | Consumables & Prep | Shop | RONA | N/A | unit |  | 20.82
garbage bags | shop | Conventional, Blindside, Caulking , CFI, XPS, Crack Injection | RONA | N/A | unit |  | 22.1
impact driver 2pack | Insulation | CFI, Blindside | RONA | N/A | unit |  | 9.98
PL 300 Glue 825ml | Insulation | CFI | RONA | N/A | tube |  | 16.49
Propane 20 lb | Consumables & Prep | Conventional, Traffic Coating | RONA | N/A | Unit |  | 23.48
sakrete concrete ( 55 lb bag) | Crack Injection | Crack Injection, Traffic Coating | RONA | N/A | unit |  | 14.75
Staples | Waterproofing | Blindside | RONA | N/A | box | 10/case | 4.79
5/16 drill bits | Insulation | CFI | RONA | N/A | unit |  | 14.99
olfa xh blades | Consumables & Prep | Conventional, Blindside, Traffic Coating, Caulking , CFI, XPS, Crack Injection | Slegg | N/A | unit |  | 29.09
Dymonic 100 (Black) | Caulking & Sealants | Conventional, Blindside, Traffic Coating, Caulking | Tremco | Cascade | Sausage |  | 8.67 | 9.55
Dymonic 100 FC (White) | Caulking & Sealants | Conventional, Blindside, Traffic Coating, Caulking | Tremco | Cascade | Sausage |  | 8.67 | 9.55
Dymonic FS cartridge | Caulking & Sealants | Caulking | Cascade | N/A | Unit |  |  |  | 60
Dymonic FS sasauges | Caulking & Sealants | Caulking | Cascade | N/A | Sausage |  |  |  | 30
Dymonic 100 (black/ grey/white) | Caulking & Sealants | Caulking | Tremco | Cascade | Sausage |  | 10.05
TremProof TP 260 55 Gallon Drum | Waterproofing | Conventional, Blindside | Tremco | Cascade | drum |  | 989.97 |  | 7
Tremco BG Grip Tape 6"x75' (8 Rolls per case) | Tanking | Blindside | Tremco | N/A | Box |  | 443.04 | 483.8
TREMCO PUMA CLEANER 6 GALLONS US | Traffic Coatings | Traffic Coating | Tremco | N/A | unit |  | 422.46 | 465.77 | 1.25
Tremco PUMA Initiator+ 10 LB PAIL | Traffic Coatings | Traffic Coating | Tremco | N/A | unit |  | 354.41 | 390.73 | 1
Tremco PUMA Primer - 2 GAL | Traffic Coatings | Traffic Coating | Tremco | N/A | unit |  | 196.6 | 216.75 | 1.25
Tremco Puma Top cat | Traffic Coatings | Traffic Coating | Tremco | N/A | unit |  | 649.88 | 716.49 | 3.1
Tremco PUMA base coat - 6 GALmb | Traffic Coatings | Traffic Coating | Tremco | N/A | unit |  | 619.88 | 683.42 | 4.1
Tremdrain 6000 | Waterproofing | Conventional | Tremco | Cascade | roll | 8 | 180 | 196.57 | 2
Tremco Drainstar 6 x50 | Waterproofing | Conventional | Tremco |  | roll |  |  |  | 15
TREMDrain 6000X 6'x50' | Blindside waterproofing | Blindside | Tremco | Cascade | roll |  | 264.26 | 288.57 | 13
TREMPROOF 250 gc 5 gallon pail | Waterproofing | Conventional | Tremco | Cascade | Unit |  |  | 249.43 | 1
TREMPROOF AMPHIBIA 5.91' X 65.62' | tanking | Conventional, Blindside | Tremco | TBD | roll |  | 1518.4 | 1658.09
UNIVERSAL TEE - PIPE (10 /CS) Drainboots | Blindside waterproofing | Traffic Coating | Tremco | TBD | unit |  | 263.23 | 308.45 | 40
VULKEM 346 Top Coat Self Leveling | Traffic Coatings | Traffic Coating | Tremco | Cascade | unit |  | 238.98 |  | 0.25
Vulkem 350 Self Leveling | Traffic Coatings | Traffic Coating | Tremco | Cascade | Unit | 36 | 290
VULKEM 350-Roller Grade 5 GAL | Traffic Coatings | Traffic Coating | Tremco | Cascade | unit |  | 238.98 | 213.73 | 8
Vulkem 351 grey - roller grade | Traffic Coatings | Traffic Coating | Tremco | Cascade | unit |  |  |  | 1
Vulkem 351 slate grey - roller grade | Traffic Coatings | Traffic Coating | Tremco | Cascade | unit
Vulkem 360 NF GREY Self Leveling 5 GAL | Traffic Coatings | Traffic Coating | Tremco | Cascade | unit |  | 285 | 243.94
Vulkem 950 NF GREY Self Leveling 15.9 lt/Kit c/w part B | Traffic Coatings | Traffic Coating | Tremco | Cascade | unit |  | 340 | 255.72
Vulkem 951 NF GREY 17.4 Ltr Kit c/w part B | Traffic Coatings | Traffic Coating | Tremco | Cascade | unit |  | 595 | 418.14 | 0.33
Vulkem Primer 191 5 GAL | Traffic Coatings | Traffic Coating | Tremco | Cascade | unit |  | 489.28 | 386.14
Delta termination bar (6 feet x 33 units per case) | Waterproofing | Conventional, Blindside | WhiteCap | Cascade | unit | 33/case | 59.94
BL526 UTILITY BRUSH BRISTLE W/RED HDL 6.5 X2X4" | Crack Injection | Crack Injection | WhiteCap | N/A | unit |  | 24.99
Bluemonster wipes | PPE | Conventional, Blindside, Traffic Coating, Crack Injection | WhiteCap | N/A | unit |  | 36
clear poly 10 x 100 | Crack Injection | Crack Injection | WhiteCap | N/A | unit |  | 37.99
Delta MS Waterproofing Membrane Drainmat 6x65.5 | Waterproofing | Conventional | WhiteCap | N/A | Roll |  |  | 168
Hydrochloric Acid 31.45 % 4L | Crack Injection | Crack Injection | WhiteCap | N/A | Unit |  | 19.5
Bosch buldg xtrm sds hammer drll bit 3/8x12" | crack injection | Crack Injection | WhiteCap |  | Unit |  | 35.99
KRYTON, KRYSTOL T1 WATERPROOFING SYSTEM GRY 25KG PAIL ( 55lb) | Crack Injection | Crack Injection | WhiteCap | N/A | unit |  | 157.99 |  | 1
DMX drainmat 6 x50 | Waterproofing | Conventional | WhiteCap |  | roll
natura seal spray seal 205 L drum F300 GE | Waterproofing | Conventional | WhiteCap | N/A | Drum |  | 1159.75 |  | 0.4
nastura seal 20 L elastomeric pail ( patching) | Waterproofing | Conventional | WhiteCap | N/A | Drum |  | 205.5 |  | 0.5
naturaflow 7000 drainmat 7.48 x 50 ' | Waterproofing | Blindside | WhiteCap | N/A | unit |  | 388 |  | 0.1
Target- Aquaplug 50 lb pail | Crack Injection | Crack Injection | WhiteCap | N/A | unit |  | 76.99
Icemelt calcluim choride 20 kg bag | Waterproofing | Blindside | WhiteCap | N/A | unit |  | 44.55
Ucan pin and washer 25 mm 1-1/2" ( 100 p box) | Waterproofing | Conventional, Blindside | WhiteCap | N/A | units |  | 29
Ucan pin and washer 25 mm 2" ( 100 p box) | Waterproofing | Conventional, Blindside | WhiteCap | N/A | units |  | 32.99
UCAN Shot for pins and washers | Waterproofing | Conventional, Blindside | WhiteCap | N/A | unit | 100/box | 29.99
Xypex Patch 'N Plug 50 lb | Crack Injection | Crack Injection | WhiteCap | N/A | Unit |  | 104.29 |  | 1
Techcrete 2" CFI 4 x2 ( 8 sqft) R 10 (3/8TH 10 MM CONCRETE TOPPING) | Insulation | CFI | WhiteCap | N/A | unit |  | 105.79 |  | 12
Techcrete 3" CFI 4x2 ( 8 sqft) R 15 | Insulation | CFI | WhiteCap | N/A | unit |  | 119.9
Techcrete 4" CFI 4x2 ( 8 sft) R 20 | Insulation | CFI | WhiteCap | N/A | unit |  | 134 |  | 5
Dow/Dupont Roofmate 35 psi xps 2" | Insulation | XPS | WhiteCap | N/A | unit |  | 21.44 |  | 9
Dow/Dupont Roofmate 35 psi xps 3" | Insulation | XPS | WhiteCap | N/A | unit |  | 32.16
Dow/Dupont Roofmate 35 psi xps 4" | Insulation | XPS | WhiteCap | N/A | unit |  | 42.88
Ramset- Insulfast 2" w fuel and 1-1/4" pin | Insulation | XPS | WhiteCap | N/A | unit | 500 p/box | 455
Ramset- Insulfast 2.5" w fuel and 1-1/4" pin | Insulation | XPS | WhiteCap | N/A | unit | 500 p/box | 455
Ramset- Insulfast 3" w fuel and 1-1/4" pin | Insulation | XPS | WhiteCap | N/A | unit | 500 p/box | 455
MSHRM Nailin ANCR Zamac Smackie | Waterproofing | Conventional, Blindside | WhiteCap | N/A | Unit | 100/box | 33

## Crew DAILY Inventory Log up to
Date | Inventory | Qty | Unit (Locked) | Action | Job | Service | Role | Crew Name
2026-06-01 | Tremdrain 6000 | 2.5 | roll | Used | Parker Jonhston- Campus View Housing 2249 McCoy St | Conventional | Assistant Tech | Shane Smith
2026-06-01 | UCAN Shot | 75 | unit | Used | Parker Jonhston- Campus View Housing 2249 McCoy St | Conventional | Assistant Tech | Shane Smith
2026-06-01 | Ucan pin and washer 25 mm 1-1/2" ( 100 p box) | 75 | unit | Used | Parker Jonhston- Campus View Housing 2249 McCoy St | Conventional | Assistant Tech | Shane Smith
2026-06-01 | CFI Panel 2" | 18 | panel | Used | ARYZE - 450 Dallas Rd | Insulation | Technician | Jon Gregoire
2026-06-01 | PL foam glue for CFI | 3 | tube | Used | ARYZE - 450 Dallas Rd | Insulation | Technician | Jon Gregoire
2026-06-01 | Dow CWS (Grey) | 2 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-02 | Ucan pin and washer 25 mm 1-1/2" ( 100 p box) | 250 | unit | Used | Avenir - Hythe, 817 Esquimalt Rd | Conventional | Assistant Tech | Shane Smith
2026-06-02 | UCAN Shot | 250 | unit | Used | Avenir - Hythe, 817 Esquimalt Rd | Conventional | Assistant Tech | Shane Smith
2026-06-02 | Tremdrain 6000 | 0.6 | roll | Used | Avenir - Hythe, 817 Esquimalt Rd | Conventional | Assistant Tech | Shane Smith
2026-06-02 | Dymonic 100 (Black) | 3 | sausage | Used | Avenir - Hythe, 817 Esquimalt Rd | Conventional | Assistant Tech | Shane Smith
2026-06-02 | Delta termination bar (6 feet x 33 units per case) | 17 | unit | Used | Avenir - Hythe, 817 Esquimalt Rd | Conventional | Assistant Tech | Shane Smith
2026-06-02 | CFI Panel 2" | 15 | panel | Used | ARYZE - 450 Dallas Rd | Insulation | Technician | Jon Gregoire
2026-06-02 | PL foam glue for CFI panels | 3 | unit | Used | ARYZE - 450 Dallas Rd | Insulation | Technician | Jon Gregoire
2026-06-02 | Dow CWS (Grey) | 1 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-03 | Tremdrain 6000 | 3 | roll | Used | Avenir - Hythe, 817 Esquimalt Rd | Conventional | Assistant Tech | Shane Smith
2026-06-03 | Ucan pin and washer 25 mm 1-1/2" ( 100 p box) | 300 | unit | Used | Avenir - Hythe, 817 Esquimalt Rd | Conventional | Assistant Tech | Shane Smith
2026-06-03 | UCAN Shot | 300 | unit | Used | Avenir - Hythe, 817 Esquimalt Rd | Conventional | Assistant Tech | Shane Smith
2026-06-03 | TremProof TP 260 55 Gallon Drum | 1 | barrel | Used | Avenir - Hythe, 817 Esquimalt Rd | Conventional | Assistant Tech | Shane Smith
2026-06-03 | Delta termination bar (6 feet x 33 units per case) | 19 | unit | Used | Avenir - Hythe, 817 Esquimalt Rd | Conventional | Assistant Tech | Shane Smith
2026-06-03 | Dap Caulking (white) | 2 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-04 | TremProof TP 260 55 Gallon Drum | 0.15 | gallon | Used | IWCD - Esquimalt Terrace | Waterproofing | Senior Tech | Jordan Thorpe
2026-06-04 | Dymonic 100 (Black) | 4 | sausage | Used | IWCD - Esquimalt Terrace | Waterproofing | Senior Tech | Jordan Thorpe
2026-06-04 | Drainstar drain mat | 1 | roll | Used | IWCD - Esquimalt Terrace | Waterproofing | Senior Tech | Jordan Thorpe
2026-06-04 | Delta termination bar (6 feet x 33 units per case) | 5 | unit | Used | IWCD - Esquimalt Terrace | Waterproofing | Senior Tech | Jordan Thorpe
2026-06-05 | Delta termination bar (6 feet x 33 units per case) | 18 | unit | Used | Orion - Aura | Waterproofing | Technician | Jon Gregoire
2026-06-05 | Dow CWS (Grey) | 3 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-08 | TREMDrain 6000X 6'x50' | 1 | roll | Used | Spire - 2300 Douglas Street | Blindside | Senior Tech | Jordan Thorpe
2026-06-08 | TremProof TP 260 55 Gallon Drum | 0.25 | barrel | Used | Spire - 2300 Douglas Street | Blindside | Senior Tech | Jordan Thorpe
2026-06-08 | Dymonic 100 (Black) | 10 | sausage | Used | Spire - 2300 Douglas Street | Blindside | Senior Tech | Jordan Thorpe
2026-06-08 | Fender Washer Plated 1/4 by 1x 1/4 | 150 | unit | Used | Spire - 2300 Douglas Street | Blindside | Senior Tech | Jordan Thorpe
2026-06-08 | Screws | 150 | unit | Used | Spire - 2300 Douglas Street | Blindside | Senior Tech | Jordan Thorpe
2026-06-08 | Injection Ports 3/8" Plastic WHITE w/Grease Fitting 100/Bag ( 318 per bag ) | 38 | unit | Used | 1315 Esquimalt Road | Crack Injection | Crew Lead | Jesse Dares
2026-06-08 | Injection Resin | 1.5 | litre | Used | 1315 Esquimalt Road | Crack Injection | Crew Lead | Jesse Dares
2026-06-08 | Seal Boss catalyst | 0.25 | cup | Used | 1315 Esquimalt Road | Crack Injection | Crew Lead | Jesse Dares
2026-06-08 | muratic acid 31.45 % 4l | 1 | cup | Used | 1315 Esquimalt Road | Crack Injection | Crew Lead | Jesse Dares
2026-06-08 | Xypex patch and plug- 50 lb | 2 | lb | Used | 1315 Esquimalt Road | Crack Injection | Crew Lead | Jesse Dares
2026-06-08 | KRYTON, KRYSTOL T1 WATERPROOFING SYSTEM GRY 25KG PAIL (55lb) | 3 | lb | Used | 1315 Esquimalt Road | Crack Injection | Crew Lead | Jesse Dares
2026-06-08 | Poly plastic protection roll | 0.25 | roll | Used | 1315 Esquimalt Road | Crack Injection | Crew Lead | Jesse Dares
2026-06-09 | Soprema Colphen BSV W (3.28' x32.8') | 3 | roll | Used | Etro - Hyatt, 1312 Broad Street | Conventional | Senior Tech | Jordan Thorpe
2026-06-09 | Soprema G10 drainmat (6*50) | 1.25 | roll | Used | Etro - Hyatt, 1312 Broad Street | Conventional | Senior Tech | Jordan Thorpe
2026-06-09 | Soprema Sopraseal Primer 19L | 2.5 | gallon | Used | Etro - Hyatt, 1312 Broad Street | Conventional | Senior Tech | Jordan Thorpe
2026-06-09 | Dap Caulking (white) | 5 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-09 | Soprema Colphen BSV W (3.28' x32.8') | 7 | roll | Used | Etro - Hyatt, 1312 Broad Street | Conventional | Senior Tech | Jordan Thorpe
2026-06-09 | Soprema G10 drainmat (6*50) | 3 | roll | Used | Etro - Hyatt, 1312 Broad Street | Conventional | Senior Tech | Jordan Thorpe
2026-06-10 | Dap Caulking (white) | 2 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-10 | Soprema Sopraseal Primer 19L | 2 | gallon | Used | Etro - Hyatt, 1312 Broad Street | Conventional | Senior Tech | Jordan Thorpe
2026-06-10 | Soprema Colphen BSV W (3.28' x32.8') | 2.5 | roll | Used | Etro - Hyatt, 1312 Broad Street | Conventional | Senior Tech | Jordan Thorpe
2026-06-10 | Soprema G10 drainmat (6*50) | 1.25 | roll | Used | Etro - Hyatt, 1312 Broad Street | Conventional | Senior Tech | Jordan Thorpe
2026-06-11 | Dap Caulking (white) | 1 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-12 | TremProof TP 260 55 Gallon Drum | 0.3 | barrel | Used | Craig White - St Michael's | Waterproofing | Technician | Jon Gregoire
2026-06-12 | Drainstar drain mat | 0.5 | roll | Used | Craig White - St Michael's | Waterproofing | Technician | Jon Gregoire
2026-06-12 | Delta termination bar (6 feet x 33 units per case) | 21 | unit | Used | Craig White - St Michael's | Waterproofing | Technician | Jon Gregoire
2026-06-12 | Pekora Dynafex - EllisDon CBH | 3 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-12 | Dap Caulking (white) | 2 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-15 | Drainstar drain mat | 2026-01-03 | roll | Used | Farmer - 11 Chown Place | Waterproofing | Technician | Josh Murray
2026-06-15 | TremProof TP 260 55 Gallon Drum | 0.1 | barrel | Used | Farmer - 11 Chown Place | Waterproofing | Technician | Josh Murray
2026-06-15 | Dap Caulking (white) | 2 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-15 | Pekora Dynafex - EllisDon CBH | 1 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-16 | Injection Ports 3/8" Plastic WHITE w/Grease Fitting 100/Bag ( 318 per bag ) | 90 | unit | Used | South Island Property Management | Crack Injection | Assistant Tech | Shane Smith
2026-06-16 | Injection Resin | 4 | litre | Used | South Island Property Management | Crack Injection | Assistant Tech | Shane Smith
2026-06-16 | Seal Boss catalyst | 1.25 | cup | Used | South Island Property Management | Crack Injection | Assistant Tech | Shane Smith
2026-06-16 | Pekora Dynafex - EllisDon CBH | 2 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-16 | Dap Caulking (white) | 3 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-17 | Soprema Colphen BSV W (3.28' x32.8') | 7 | roll | Used | Etro - Hyatt, 1312 Broad Street | Conventional | Senior Tech | Jordan Thorpe
2026-06-17 | Soprema G10 drainmat (6*50) | 2 | roll | Used | Etro - Hyatt, 1312 Broad Street | Conventional | Senior Tech | Jordan Thorpe
2026-06-17 | Dap Caulking (white) | 3 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-17 | Dymonic 100 FC (White) | 3 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-17 | VULKEM 350-R 5 GAL | 4 | pail | Used | South Island Property Management | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-06-17 | Vulkem Primer 191 5 GAL | 0.5 | gallon | Used | South Island Property Management | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-06-17 | Roller Sleeves | 1 | unit | Used | South Island Property Management | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-06-18 | VULKEM 346 TC SL | 4.5 | pail | Used | South Island Property Management | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-06-18 | Vulkem Primer 191 5 GAL | 0.5 | gal | Used | South Island Property Management | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-06-18 | Roller Sleeves | 2 | unit | Used | South Island Property Management | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-06-18 | WIZZ Roller Sleeves | 2 | unit | Used | South Island Property Management | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-06-18 | Xylene 4L | 0.5 | gal | Used | South Island Property Management | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-06-18 | Rags | 0.5 | bag | Used | South Island Property Management | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-06-18 | Gloves | 1 | box | Used | South Island Property Management | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-06-19 | CFI Panel 2" | 10 | panel | Used | ARYZE - 450 Dallas Rd | Insulation | Senior Tech | Jordan Thorpe
2026-06-19 | PL foam glue for CFI | 2 | tube | Used | ARYZE - 450 Dallas Rd | Insulation | Senior Tech | Jordan Thorpe
2026-06-19 | Dow CWS (Grey) | 1 | unit | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-19 | Dap Caulking (white) | 3 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-19 | XPS 2" Insulation | 42 | unit | used | Unitech - Crofton | Insulation | Technician | Jon Gregoire
2026-06-19 | Drainstar drain mat | 2 | roll | used | Unitech - Crofton | Insulation | Technician | Jon Gregoire
2026-06-19 | Delta termination bar (6 feet x 33 units per case) | 48 | unit | used | Unitech - Crofton | Insulation | Technician | Jon Gregoire
2026-06-19 | Injection Resin | 1 | litre | Used | 955 Jasmine | Crack Injection | Crew Lead | Jesse Dares
2026-06-19 | Seal Boss catalyst | 1.5 | cup | Used | 955 Jasmine | Crack Injection | Crew Lead | Jesse Dares
2026-06-19 | KRYTON, KRYSTOL T1 WATERPROOFING SYSTEM GRY 25KG PAIL (55lb) | 1 | lb | Used | 955 Jasmine | Crack Injection | Crew Lead | Jesse Dares
2026-06-19 | Xypex patch and plug- 50 lb | 2 | lb | Used | 955 Jasmine | Crack Injection | Crew Lead | Jesse Dares
2026-06-19 | Injection Ports 3/8" Plastic WHITE w/Grease Fitting 100/Bag ( 318 per bag ) | 7 | unit | Used | 955 Jasmine | Crack Injection | Crew Lead | Jesse Dares
2026-06-20 | TremProof TP 260 55 Gallon Drum | 1.5 | barrel | Used | Parker Jonhston- Campus View Housing 2249 McCoy St | Waterproofing | Senior Tech | Jordan Thorpe
2026-06-20 | Drainstar drain mat | 4.25 | roll | Used | Parker Jonhston- Campus View Housing 2249 McCoy St | Waterproofing | Senior Tech | Jordan Thorpe
2026-06-22 | Dymonic 100 (Black) | 1 | sausage | Used | Parker Jonhston- Campus View Housing 2249 McCoy St | Waterproofing | Senior Tech | Jordan Thorpe
2026-06-22 | CFI Panel 2" | 22 | panel | Used | ARYZE - 450 Dallas Rd | Insulation | Technician | Jon Gregoire
2026-06-22 | PL foam glue for CFI | 2 | tube | Used | ARYZE - 450 Dallas Rd | Insulation | Technician | Jon Gregoire
2026-06-22 | Dow CWS (Grey) | 1 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-22 | Dap Caulking (white) | 3 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-23 | Dow CWS (Grey) | 3 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-23 | Dymonic 100 FC (White) | 3 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-24 | TremProof TP 260 55 Gallon Drum | 0.1 | barrel | Used | Path - TH East | Waterproofing | Technician | Josh Murray
2026-06-24 | Drainstar drain mat | 33.3 | roll | Used | Path - TH East | Waterproofing | Technician | Josh Murray
2026-06-24 | UCAN Shot | 100 | unit | Used | Path - TH East | Waterproofing | Technician | Josh Murray
2026-06-24 | Ucan pin and washer 25 mm 1-1/2" ( 100 p box) | 100 | unit | Used | Path - TH East | Waterproofing | Technician | Josh Murray
2026-06-24 | Injection Rope | 2 | foot | Used | Bay Centre - TK Elevators | Crack Injection | Crew Lead | Jesse Dares
2026-06-24 | Sealboss oakum (7 x1 ft bag) | 1 | foot | Used | Bay Centre - TK Elevators | Crack Injection | Crew Lead | Jesse Dares
2026-06-24 | sakrete concrete ( 55 lb bag) | 2 | bag | Used | Bay Centre - TK Elevators | Crack Injection | Crew Lead | Jesse Dares
2026-06-25 | CFI Panel 2" | 30 | panel | Used | ARYZE - 450 Dallas Rd | Insulation | Technician | Jon Gregoire
2026-06-25 | PL foam glue for CFI | 3 | tube | Used | ARYZE - 450 Dallas Rd | Insulation | Technician | Jon Gregoire
2026-06-25 | Dymonic 100 FC (White) | 1 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-26 | TremProof TP 260 55 Gallon Drum | 1.5 | barrel | Used | Blackcrete - 814 Hockley Ave | Waterproofing | Technician | Josh Murray
2026-06-26 | Tremdrain 6000 | 1.25 | roll | Used | Blackcrete - 814 Hockley Ave | Waterproofing | Technician | Josh Murray
2026-06-26 | Injection Resin | 1 | litre | Used | Bay Centre - TK Elevators | Crack Injection | Crew Lead | Jesse Dares
2026-06-26 | Seal Boss catalyst | 1.5 | cup | Used | Bay Centre - TK Elevators | Crack Injection | Crew Lead | Jesse Dares
2026-06-26 | Dymonic 100 FC (White) | 2 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-29 | TREMPROOF 250 gc 5 gallon pail | 6 | pail | Used | Etro - Hyatt, 1312 Broad Street (AKA Durwest) | Conventional | Assistant Tech | Logan Pardy
2026-06-29 | Dow CWS (Grey) | 2 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-06-30 | TREMDrain 6000X 6'x50' | 1 | roll | Used | Spire - 2300 Douglas Street | Blindside | Technician | Jon Gregoire
2026-06-30 | Dymonic 100 (Black) | 5 | tube | Used | Spire - 2300 Douglas Street | Blindside | Technician | Jon Gregoire
2026-06-30 | TremProof TP 260 55 Gallon Drum | 33.3 | gallon | Used | Spire - 2300 Douglas Street | Blindside | Technician | Jon Gregoire
2026-07-02 | Dymonic 100 FC (White) | 3 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-02 | Pekora Dynafex - EllisDon CBH | 3 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-03 | VULKEM 346 TC SL | 1.25 | pail | Used | Keefer Deck | Traffic Coatings | Technician | Jon Gregoire
2026-07-03 | Vulkem Primer 191 5 GAL | 0.25 | pail | Used | Keefer Deck | Traffic Coatings | Technician | Jon Gregoire
2026-07-03 | Xylene 4L | 0.5 | gallon | Used | Keefer Deck | Traffic Coatings | Technician | Jon Gregoire
2026-07-03 | Dymonic 100 FC (White) | 4 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-08 | TremProof TP 260 55 Gallon Drum | 33.3 | barrel | Used | Parker Jonhston- Campus View Housing 2249 McCoy St | Conventional | Technician | Josh Murray
2026-07-08 | Drainstar drain mat | 1 | rol | Used | Parker Jonhston- Campus View Housing 2249 McCoy St | Conventional | Technician | Josh Murray
2026-07-08 | Dymonic 100 (Black) | 4 | tube | Used | Frontera - 958 W | Traffic Coatings | Crew Lead | Jesse Dares
2026-07-08 | Soprema Alsan flashing 19 l | 0.5 | pail | Used | Etro - Hyatt, 1312 Broad Street (AKA Durwest) | Conventional | Assistant Tech | Logan Pardy
2026-07-08 | Propane 20 lb | 1 | unit | Used | Etro - Hyatt, 1312 Broad Street (AKA Durwest) | Conventional | Assistant Tech | Logan Pardy
2026-07-08 | VULKEM 346 TC SL | 33.3 | pail | Used | Reid Deck - 321 Simcoe | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-07-08 | Sand | 1 | bag | Used | Reid Deck - 321 Simcoe | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-07-08 | Xylene 4L | 0.5 | gallon | Used | Reid Deck - 321 Simcoe | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-07-08 | Roller Sleeves | 2 | unit | Used | Reid Deck - 321 Simcoe | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-07-08 | WIZZ Roller Sleeves | 2 | unit | Used | Reid Deck - 321 Simcoe | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-07-08 | pelican pail liner | 2 | unit | Used | Reid Deck - 321 Simcoe | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-07-08 | Paint Brushes | 2 | unit | Used | Reid Deck - 321 Simcoe | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-07-08 | Rags | 0.25 | bag | Used | Reid Deck - 321 Simcoe | Traffic Coatings | Senior Tech | Jordan Thorpe
2026-07-08 | Dow CWS (Grey) | 3 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-08 | Dymonic 100 FC (White) | 1 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-09 | TremProof TP 260 55 Gallon Drum | 1.5 | barrel | Used | Blackcrete - 814 Hockley Ave | Waterproofing | Technician | Josh Murray
2026-07-09 | Tremdrain 6000 | 2 | roll | Used | Blackcrete - 814 Hockley Ave | Waterproofing | Technician | Josh Murray
2026-07-09 | Soprema Alsan flashing 19 l | 0.5 | pail | Used | Etro - Hyatt, 1312 Broad Street (AKA Durwest) | Conventional | Assistant Tech | Logan Pardy
2026-07-09 | paint Brushes | 1 | unit | Used | Etro - Hyatt, 1312 Broad Street (AKA Durwest) | Conventional | Assistant Tech | Logan Pardy
2026-07-09 | Dymonic 100 (Black) | 1 | tube | Used | Etro - Hyatt, 1312 Broad Street (AKA Durwest) | Conventional | Assistant Tech | Logan Pardy
2026-07-09 | Dow CWS (Grey) | 3 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-09 | Dymonic 100 FC (White) | 1 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-10 | Ucan pin and washer 25 mm 1-1/2" ( 100 p box) | 40 | unit | Used | Axiom - Bellweather, 135 Gorge Rd Est | Waterproofing | Technician | Josh Murray
2026-07-10 | UCAN Shot | 40 | unit | Used | Axiom - Bellweather, 135 Gorge Rd Est | Waterproofing | Technician | Josh Murray
2026-07-10 | TremProof TP 260 55 Gallon Drum | 2026-01-08 | barrel | Used | Axiom - Bellweather, 135 Gorge Rd Est | Waterproofing | Technician | Josh Murray
2026-07-10 | VULKEM 346 TC SL | 2026-03-05 | pail | Used | Frontera - 958 W | Traffic Coatings | Technician | Jon Gregoire
2026-07-10 | VULKEM 350-R 5 GAL | 1 | pail | Used | Frontera - 958 W | Traffic Coatings | Technician | Jon Gregoire
2026-07-10 | Roller Sleeves | 2 | unit | Used | Frontera - 958 W | Traffic Coatings | Technician | Jon Gregoire
2026-07-10 | WIZZ Roller Sleeves | 4 | unit | Used | Frontera - 958 W | Traffic Coatings | Technician | Jon Gregoire
2026-07-10 | Xylene 4L | 1 | gallon | Used | Frontera - 958 W | Traffic Coatings | Technician | Jon Gregoire
2026-07-10 | pelican pail liner | 4 | unit | Used | Frontera - 958 W | Traffic Coatings | Technician | Jon Gregoire
2026-07-10 | Dymonic 100 FC (White) | 2 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-10 | Dow CWS (Grey) | 3 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-13 | Drainstar drain mat | 2026-03-04 | roll | Used | Kinetic - CRD 2995 Sooke Road | Insulation | Technician | Josh Murray
2026-07-13 | TremProof TP 260 55 Gallon Drum | 2026-01-04 | barrel | Used | Kinetic - CRD 2995 Sooke Road | Insulation | Technician | Josh Murray
2026-07-13 | Ucan pin and washer 25 mm 1-1/2" ( 100 p box) | 25 | unit | Used | Kinetic - CRD 2995 Sooke Road | Insulation | Technician | Josh Murray
2026-07-13 | UCAN Shot | 25 | unit | Used | Kinetic - CRD 2995 Sooke Road | Insulation | Technician | Josh Murray
2026-07-13 | Dow CWS (Grey) | 4 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-13 | Dymonic 100 FC (White) | 2 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-14 | Drainstar drain mat | 1 | roll | Used | Farmer - 11 Chown Place | Waterproofing | Technician | Jon Gregoire
2026-07-14 | Dymonic 100 (Black) | 1 | tube | Used | Farmer - 11 Chown Place | Waterproofing | Technician | Jon Gregoire
2026-07-14 | Delta termination bar (6 feet x 33 units per case) | 6 | unit | Used | Farmer - 11 Chown Place | Waterproofing | Technician | Jon Gregoire
2026-07-14 | XPS 2" Insulation | 30 | unit | Used | Kinetic - CRD 2995 Sooke Road | Insulation | Assistant Tech | Logan Pardy
2026-07-14 | Ramset 2" insulation pins | 40 | unit | Used | Kinetic - CRD 2995 Sooke Road | Insulation | Assistant Tech | Logan Pardy
2026-07-14 | Drainstar drain mat | 0.5 | roll | Used | Kinetic - CRD 2995 Sooke Road | Insulation | Assistant Tech | Logan Pardy
2026-07-14 | TremProof TP 260 55 Gallon Drum | 0.25 | barrel | Used | Kinetic - CRD 2995 Sooke Road | Insulation | Assistant Tech | Logan Pardy
2026-07-14 | Dow CWS (Grey) | 4 | sausage | Used | Assa Abloy - Cow Bay Hosp, 6775 Bell | Caulking | Caulker | Bobby Wagner
2026-07-14 | Dymonic 100 FC (White) | 2 | sausage | Used | Assa Abloy - Cow Bay Hosp, 6775 Bell | Caulking | Caulker | Bobby Wagner
2026-07-15 | Ucan pin and washer 25 mm 1-1/2" ( 100 p box) | 44 | unit | Used | Path - TH East | Waterproofing | Assistant Tech | Logan Pardy
2026-07-15 | UCAN Shot | 44 | unit | Used | Path - TH East | Waterproofing | Assistant Tech | Logan Pardy
2026-07-15 | TremProof TP 260 55 Gallon Drum | 0.25 | gallon | Used | Path - TH East | Waterproofing | Assistant Tech | Logan Pardy
2026-07-15 | Delta termination bar (6 feet x 33 units per case) | 11 | unit | Used | Path - TH East | Waterproofing | Assistant Tech | Logan Pardy
2026-07-15 | Dow CWS (Grey) | 6 | sausage | Used | Assa Abloy - Cow Bay Hosp, 6775 Bell | Caulking | Caulker | Bobby Wagner
2026-07-16 | TremProof TP 260 55 Gallon Drum | 2 | barrel | Used | Farmer - Verdier | Waterproofing | Technician | Josh Murray
2026-07-16 | Dymonic 100 FC (White) | 6 | tube | Used | Farmer - Verdier | Waterproofing | Technician | Josh Murray
2026-07-16 | Ucan pin and washer 25 mm 1-1/2" ( 100 p box) | 75 | unit | Used | Farmer - Verdier | Waterproofing | Technician | Josh Murray
2026-07-16 | UCAN Shot | 75 | unit | Used | Farmer - Verdier | Waterproofing | Technician | Josh Murray
2026-07-16 | Drainstar drain mat | 5.75 | roll | Used | Farmer - Verdier | Waterproofing | Technician | Josh Murray
2026-07-16 | Dymonic 100 FC (White) | 9 | tube | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-16 | Dow CWS (Grey) | 2 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-17 | Dymonic 100 FC (White) | 3 | tube | Used | Parker Jonhston- Campus View Housing 2249 McCoy St | Conventional | Technician | Jon Gregoire
2026-07-17 | Ucan pin and washer 25 mm 1-1/2" ( 100 p box) | 100 | unit | Used | Parker Jonhston- Campus View Housing 2249 McCoy St | Conventional | Technician | Jon Gregoire
2026-07-17 | UCAN Shot | 100 | unit | Used | Parker Jonhston- Campus View Housing 2249 McCoy St | Conventional | Technician | Jon Gregoire
2026-07-17 | Drainstar drain mat | 0.5 | roll | Used | Parker Jonhston- Campus View Housing 2249 McCoy St | Conventional | Technician | Jon Gregoire
2026-07-17 | Injection Ports 3/8" Plastic WHITE w/Grease Fitting 100/Bag ( 318 per bag ) | 190 | unit | Used | WestUrban - Erskine | Crack Injection | Assistant Tech | Logan Pardy
ITEMS BELOW ARE NEW as of Aug 4
2026-07-20 |  |  |  | Used | Orion - Impera, 797 Revilo Place | Waterproofing | Technician | Josh Murray
2026-07-20 |  |  |  | Used | Orion - Impera, 797 Revilo Place | Waterproofing | Technician | Josh Murray
2026-07-20 | dymonic 100 grey | 3 | box | Used | Knappett - Qualicum Beach Elem, 699 Claymore Rd W |  | Senior Tech | Jordan Thorpe
2026-07-20 | Backer Rod | 0.5 | roll | Used | Knappett - Qualicum Beach Elem, 699 Claymore Rd W |  | Senior Tech | Jordan Thorpe
2026-07-20 | Rags | 0.5 | bag | Used | Knappett - Qualicum Beach Elem, 699 Claymore Rd W |  | Senior Tech | Jordan Thorpe
2026-07-20 |  |  |  | Used | WestUrban, Erskine, 15 Erskine Lane |  | Assistant Tech | Logan Pardy
2026-07-20 |  |  |  | Used | WestUrban, Erskine, 15 Erskine Lane |  | Assistant Tech | Logan Pardy
2026-07-20 |  |  |  | Used | WestUrban, Erskine, 15 Erskine Lane |  | Assistant Tech | Logan Pardy
2026-07-20 |  |  |  | Used | WestUrban, Erskine, 15 Erskine Lane |  | Assistant Tech | Logan Pardy
2026-07-21 |  |  |  | Used | WestUrban, Erskine, 15 Erskine Lane |  | Assistant Tech | Logan Pardy
2026-07-21 |  |  |  | Used | WestUrban, Erskine, 15 Erskine Lane |  | Assistant Tech | Logan Pardy
2026-07-21 |  |  |  | Used | WestUrban, Erskine, 15 Erskine Lane |  | Assistant Tech | Logan Pardy
2026-07-21 | CWS White | 5 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd |  | Caulker | Bobby Wagner
2026-07-21 | Dymonic 100 FC (White) | 7 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd |  | Caulker | Bobby Wagner
2026-07-22 |  |  |  | Used | Farmer - 11 Chown Place |  | Technician | Jon Gregoire
2026-07-22 |  |  |  | Used | Farmer - 11 Chown Place |  | Technician | Jon Gregoire
2026-07-22 | Kryton | 0.25 | unit | Used | WestUrban, Erskine, 15 Erskine Lane |  | Assistant Tech | Logan Pardy
2026-07-22 | Xypex |  |  | Used | WestUrban, Erskine, 15 Erskine Lane |  | Assistant Tech | Logan Pardy
2026-07-22 | CWS White | 1 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-22 | Dymonic 100 FC (White) | 2 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-23 |  |  |  |  | WestUrban, Erskine, 15 Erskine Lane | Crack Injection | Assistant Tech | Logan Pardy
2026-07-23 | CWS White | 5 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd |  | Caulker | Bobby Wagner
2026-07-23 | Dymonic 100 FC (White) | 1 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd |  | Caulker | Bobby Wagner
2026-07-24 | Naturaseal GE | 0.33 | barrel | Used | Parkshore,Gibbins, 3096 Gibbins Road | Waterproofing | Technician | Josh Murray
2026-07-24 | naturaseal 7000 | 2 | Rolls | Used | Parkshore,Gibbins, 3096 Gibbins Road | Waterproofing | Technician | Josh Murray
2026-07-24 | CWS White | 2 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-24 | Dymonic 100 FC (White) | 2 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-27 | Grease Fittings | 14 | Unit | Used | WestUrban, Erskine, 15 Erskine Lane | Crack Injection | Assistant Tech | Logan Pardy
2026-07-27 | Xypex | 0.25 | Unit | Used | WestUrban, Erskine, 15 Erskine Lane | Crack Injection | Assistant Tech | Logan Pardy
2026-07-27 | Kryton | 0.25 | Unit | Used | WestUrban, Erskine, 15 Erskine Lane | Crack Injection | Assistant Tech | Logan Pardy
2026-07-27 | Foam | 2 | Unit | Used | WestUrban, Erskine, 15 Erskine Lane | Crack Injection | Assistant Tech | Logan Pardy
2026-07-27 | 4oz 44 mm of acceleration |  | Unit | Used | WestUrban, Erskine, 15 Erskine Lane | Crack Injection | Assistant Tech | Logan Pardy
2026-07-27 | CWS Grey | 5 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-28 | Tremdrain | 4 | roll | Used | Farmer - Verd Affordable Housing, 1183 Verdier Ave | Waterproofing | Technician | Josh Murray
2026-07-28 | Drain star | 1 | roll | Used | David Haydar - 1779 Falcon heights | Waterproofing | Technician | Jon Gregoire
2026-07-28 | Term Bar | 5 | unit | Used | David Haydar - 1779 Falcon heights | Waterproofing | Technician | Jon Gregoire
2026-07-28 | Pin & Shots |  |  | Used | David Haydar - 1779 Falcon heights | Waterproofing | Technician | Jon Gregoire
2026-07-28 | CWS Grey | 4 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-28 | Dymonic 100 FC (White) | 1 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
| Drain mat | 8 | rolls | Used | Blackcrete - 814 Hockley Ave | Waterproofing | Crew Lead | Jesse Dares
2026-07-29 | Pins | 4 | boxes | Used | Blackcrete - 814 Hockley Ave | Waterproofing | Crew Lead | Jesse Dares
2026-07-29 | Caulking | 19 | sausage | Used | Blackcrete - 814 Hockley Ave | Waterproofing | Crew Lead | Jesse Dares
2026-07-29 | Glue | 2.5 | Unit | Used | Blackcrete - 814 Hockley Ave | Waterproofing | Crew Lead | Jesse Dares
2026-07-29 |  |  |  |  | WestUrban, Erskine, 15 Erskine Lane |  | Assistant Tech | Logan Pardy
2026-07-29 |  |  |  |  | WestUrban, Erskine, 15 Erskine Lane |  | Assistant Tech | Logan Pardy
2026-07-29 |  |  |  |  | WestUrban, Erskine, 15 Erskine Lane |  | Assistant Tech | Logan Pardy
2026-07-29 |  |  |  |  | WestUrban, Erskine, 15 Erskine Lane |  | Assistant Tech | Logan Pardy
2026-07-28 | CWS White | 3 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-29 | Dymonic 100 FC (White) | 1 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-30 | 6000x | 7 | rolls | Used | Blackcrete - 814 Hockley Ave | Waterproofing | Technician | Josh Murray
2026-07-30 | Pin & Shots | 2 | Box | Used | Blackcrete - 814 Hockley Ave | Waterproofing | Technician | Josh Murray
2026-07-30 | Screws & Washer | 100 | Units | Used | Blackcrete - 814 Hockley Ave | Waterproofing | Technician | Josh Murray
2026-07-30 | CWS White | 2 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-30 | Dymonic 100 FC (White) | 2 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-31 | CWS White | 6 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-31 | Dymonic 100 FC (White) | 1 | sausage | Used | EllisDon - Cow Bay Hospital, 6775 Bell McKinnon Rd | Caulking | Caulker | Bobby Wagner
2026-07-31 | No details logged for Chandos NC job

## Tools
Tool ID | Tool | Service | Status | Condition | Battery? | Last Charged | Out With | Out Job | Notes
t1 | Propane Torch Kit | Waterproofing | In | Good | No |  | You
t2 | Hot Air Welder | Waterproofing | Out | Good | No |  | You | Blackcrete — 814 Hockley Ave
t3 | Seam Roller Set | Waterproofing | In | Good | No |  | You
t4 | Cordless Impact Driver | Insulation | In | Good | Yes | 2026-07-16 | You
t5 | Hot Knife | Insulation | In | In repair | No |  | You |  | Element intermittent
t6 | Foam Applicator Gun | Insulation | In | Good | No |  | You
t7 | Injection Pump | Crack Injection | Out | Good | No |  | You | Spire — 2300 Douglas St
t8 | Cordless Hammer Drill | Crack Injection | Out | Good | Yes | 2026-07-15 | You | Spire — 2300 Douglas St
t9 | Airless Sprayer | Traffic Coatings | In | Damaged | No |  | You |  | Tip guard cracked
t10 | Cordless Angle Grinder | Traffic Coatings | In | Good | Yes | 2026-07-13 | You
t11 | Spike Shoes (pair) | Traffic Coatings | In | Good | No |  | You
t12 | Generator 3500W | Vehicle / General | In | Good | No |  | You
t13 | Pressure Washer | Vehicle / General | In | Good | No |  | You
t14 | Cordless Drill #1 | Vehicle / General | In | Good | Yes | 2026-07-16 | You
t15 | Cordless Drill #2 | Vehicle / General | Out | Good | Yes | 2026-07-14 | You | Blackcrete — 814 Hockley Ave
t16 | LED Work Lights | Vehicle / General | In | Good | Yes | 2026-07-12 | You
t17 | Extension Ladder 24' | Vehicle / General | In | Good | No |  | You
t18 | Wet/Dry Vac | Vehicle / General | In | Good | No |  | You
t19
t20
t21
t22
t23
t24
t25
t26
t27
t28
t29
t30
t31
t32
t33
t34
t35
t36
t37
t38
t39

## Trucks (Ready)
Show to crew | Make | Model | Model Year | VIN | Registration | License Plate # | Insurance Policy # | Current KM | Last Serviced | Last Oil Change (KM)
Y | FORD TRUCK/VAN | F150 XL SUPERCAB 4WD | 2011 | 1FTFX1EF0BFC74422 | 10349554 | LY1180 | 4V.AUM
N | MAZDA | CX-90 GT PHEV 4DR AWD | 2025 | JM3KKDHA2S1230991 | 14980389 | XG901N | AM.PVM
Y | TOYOTA | Dyna (Right Hand Drive) | 1990 | LY610027778 | 02102787 | XP1329 | BE.O5T
Y | DODGE/RAM TRUCK/VAN | RAM 2500 SLT REG CAB 2WD | 2008 | 3D7KR26D48G240802 | 03204006 | WB5878 | A9.CU0
Y | FORD | Other Type 2 2Whdrs | 2001 | 1FDXE45S31HB68733 | 00784663 | KH2916 | 4T.LR7
Y | CHEVROLET TRUCK/VAN | ASTRO CARGO VAN EXT 2WD | 1998 | 1GCDM19W9WB151127 | 04939380 | KH2918 | 4T.LRN
Y | FORD | E350 Club Wagon | 2000 | 1FDWE35L4YHA92089 | 00266505 | KH2919 | 4T.LRW

## Truck Tasks
UpdatedsAug 6 | Task | Service | Reset Cycle | Time Of Day | Person Responsible | Points
| Record ending KM | Vehicle / General | Daily | End-Of-Day |  | 5
NEW | Gas tank at least 50% full BEFORE dropping off truck | Vehicle / General | Daily | End-Of-Day |  | 5
NEW | Gas tank at least 50% full BEFORE going to job site | Vehicle / General | Daily | Start-Of-Day |  | 5
| Lube spray hog piston | Vehicle / General | Daily | Start-Of-Day
| Flush spray hose lines | Vehicle / General | Monthly | Start-Of-Day
| Check tar and calcium hoses for leaks | Vehicle / General | Monthly | Start-Of-Day
| Unspool tar and calcuim line and check for holes or cuts | Vehicle / General | Monthly | Start-Of-Day
| Sweep interior box truck floor | Vehicle / General | Weekly | Start-Of-Day
| All items in put back in their place | Vehicle / General | Daily | End-Of-Day
| Check Oil | Vehicle / General | Monthly | Start-Of-Day |  | 5
| Coolant & washer fluid check | Vehicle / General | Monthly | Start-Of-Day |  | 5
| Check Brake Fluid | Vehicle / General | Monthly | Start-Of-Day |  | 5
| Check Tire Pressure | Vehicle / General | Monthly | Start-Of-Day |  | 5
| Check head/ tail lights | Vehicle / General | Monthly | Start-Of-Day |  | 5
| Oil change service | Vehicle / General | Quarterly | Start-Of-Day |  | 5
| Tire rotation service | Vehicle / General | Yearly | Start-Of-Day |  | 5
| Suspension service | Vehicle / General | Yearly | Start-Of-Day |  | 5
| complete mechanical inspection | Vehicle / General | As-Needed | Start-Of-Day |  | 5
| Critical fluid servicing | Vehicle / General | Yearly | End-Of-Day |  | 5
| Fire extinguisher & first-aid, eye flush checked | Vehicle / General | Quarterly | Start-Of-Day |  | 5
| All personal items removed from truck | Vehicle / General | Daily | End-Of-Day
| gabage removed from box and cab | Vehicle Cleaning | Daily | End-Of-Day |  | 5
| interior cab surfaced wiped down | Vehicle Cleaning | Daily | End-Of-Day |  | 5
| windshield cleaned | Vehicle Cleaning | Weekly | Start-Of-Day |  | 5
| exterior pressure washed | Vehicle Cleaning | Monthly | Start-Of-Day |  | 5
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies

## Tool Log (In Progress) (hidden)
Date | Tool | Action | Job | Service | Crew | Notes | Points Earned
2026-07-15 | Injection Pump | Checked out | Spire — 2300 Douglas St | Crack Injection | You | example | 5
2026-07-16 | Cordless Impact Driver | Charged |  |  | You | battery topped up | 5
2026-07-14 | Airless Sprayer | Damage |  |  | You | Tip guard cracked | 5
[5 empty] | You |  | 5
2026-07-20 |  |  |  |  | You |  | 5
2026-07-21 |  |  |  |  | You |  | 5
2026-07-22 |  |  |  |  | You |  | 5
2026-07-23 |  |  |  |  | You |  | 5
2026-07-24 |  |  |  |  | You |  | 5
2026-07-25 |  |  |  |  | You |  | 5
2026-07-26 |  |  |  |  | You |  | 5
2026-07-27 |  |  |  |  | You |  | 5
2026-07-28 |  |  |  |  | You |  | 5
2026-07-29 |  |  |  |  | You |  | 5
2026-07-30 |  |  |  |  | You |  | 5
2026-07-31 |  |  |  |  | You |  | 5
2026-08-01 |  |  |  |  | You |  | 5
2026-08-02 |  |  |  |  | You |  | 5
2026-08-03 |  |  |  |  | You |  | 5
2026-08-04 |  |  |  |  | You |  | 5
2026-08-05 |  |  |  |  | You |  | 5
2026-08-06 |  |  |  |  | You |  | 5
2026-08-07 |  |  |  |  | You |  | 5
2026-08-08 |  |  |  |  | You |  | 5
2026-08-09 |  |  |  |  | You |  | 5
2026-08-10 |  |  |  |  | You |  | 5
2026-08-11 |  |  |  |  | You |  | 5
2026-08-12 |  |  |  |  | You |  | 5
2026-08-13 |  |  |  |  | You |  | 5
2026-08-14 |  |  |  |  | You |  | 5
2026-08-15 |  |  |  |  | You |  | 5
2026-08-16 |  |  |  |  | You |  | 5
2026-08-17 |  |  |  |  | You |  | 5
2026-08-18 |  |  |  |  | You |  | 5
2026-08-19
2026-08-20
2026-08-21
2026-08-22
2026-08-23
2026-08-24
2026-08-25
2026-08-26
2026-08-27
2026-08-28
2026-08-29
2026-08-30
2026-08-31

## Truck Gas Station Logs (Ready)
Date | Truck | Odometer KM | Driver | Gas Station | Fuel Topped | Total Charge with GST | Gas Only | Fuel Topped | Exterior Wash | Repairs / Issues | Notes | PHOTO | Points Earned
2026-07-16 | Truck 1 — Ford F-350 | 184300 | You |  | Yes |  |  | Yes | Yes |  | Ex. Purchased a drink or snack | Need to be able to add a photo of their receipt | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
|  |  | You | [9 empty] | 5
5
5

## Warehouse Tasks
| Task | Service | Reset Cycle | Time Of Day | Person Responsible | Points
| bathroom garbage removed | Bathroom | Weekly | End-Of-Day |  | 5
| toilet cleaned inside and out | Bathroom | Weekly | End-Of-Day |  | 5
| sink cleaned | Bathroom | Weekly | End-Of-Day |  | 5
| mirror cleaned | Bathroom | Weekly | End-Of-Day |  | 5
| toilet paper replaced | Bathroom | Weekly | End-Of-Day |  | 5
| Shelves oragnized to match pictures on racks | Inventory | Daily | End-Of-Day |  | 5
| tar barrels screened | Inventory | Monthly | End-Of-Day |  | 5
| check for cuts and tears on electrial cords | Inventory | Monthly | End-Of-Day |  | 5
| Verify Minimum Stock on cosumables and ppe | Inventory | Weekly | End-Of-Day | Crew Lead | 5
| Remove Damaged Inventory | Inventory | Weekly | End-Of-Day | Crew Lead | 5
| Full inventory, tool, trucks & trailer audit | Inventory | Quarterly | End-Of-Day | Crew Lead | 5
| Monday inventory purchasing review and order two weeks out | Materials | Weekly | End-Of-Day | Crew Lead | 5
| defective tools tagged with Red tag and put into fix area | Shop | Daily | Start-Of-Day |  | 5
| Garbage taken to hartland dump only | Shop Cleaning | Weekly | End-Of-Day |  | 5
| black desk free of garbage and materials , and wiped down | Shop Cleaning | Weekly | End-Of-Day |  | 5
| garbage bagged up sorted and in pile | Shop Cleaning | Daily | End-Of-Day |  | 5
| shop floor mopped | Shop Cleaning | Monthly | End-Of-Day |  | 5
| shop floor swept | Shop Cleaning | Monthly | End-Of-Day |  | 5
| removal of coating from traffic coating spikes | Tools/ Material Clea | As-Needed | End-Of-Day |  | 5
| power tools and betteries inspected, tested and cleaned | Tools/ Material Clea | Daily | End-Of-Day |  | 5
| scaffolding castors cleaned | Tools/ Material Clea | Monthly | End-Of-Day |  | 5
| caulking slicks cleaned | Tools/ Material Clea | Daily | End-Of-Day |  | 5
| caulking guns cleaned | Tools/ Material Clea | Daily | End-Of-Day |  | 5
| tar gun cleaned | Tools/ Material Clea | Daily | Start-Of-Day |  | 5
| Greyco Acid flush pump | Tools/ Material Clea | Daily | End-Of-Day |  | 5
| Monthly Inventory Count updated in App | Shop | Monthly | End-Of-Day | Crew Lead
| Complete daily inventory log | Inventory | Daily | End-Of-Day
NEW | Assign crew member to login to Warehouse Wizard and complete daily checks | Shop | Daily | Start-Of-Day
NEW | Assign crew member to login to Warehouse Wizard and complete daily checks | Shop | Daily | End-Of-Day
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies
Task
Materials loaded
Tools loaded
Batteries charged
PPE
Site protection
Cleanup supplies

## Service Load InLoad Out
Task ID | Task | Service | Reset Cycle
| 3/8th hammer drill bit | CFI | Daily
| Hilti TE 35 hammer drill | Crack Injection | Daily
| Hiti VC 150 vacum | Crack Injection | Daily
| Seal boss injection pump | Crack Injection | Daily
| Injection Ports 3/8" Plastic WHITE w/Grease Fitting 100/Bag ( 318 per bag ) | Crack Injection | Daily
| SealBoss 15X Accelerator for 1510/1570 .5 gal ( 1.89 l/ 8 CUPS ) | Crack Injection | Daily
| SealBoss 1570 PU Injection Grout 5 gal ( 18.9 L) | Crack Injection | Daily
| KRYSTOL T1 WATERPROOFING SYSTEM GRY 25KG PAIL ( 55lb) | Crack Injection | Daily
| Traffic Coatings Drill and mixing paddle | Crack Injection | Daily
| 15 L mixing buckets | Crack Injection | Daily
| Load injection pump, ports & resin | Crack Injection | Daily
| Xypex / Kryton & catalyst loaded | Crack Injection | Daily
| BL526 UTILITY BRUSH 6.5 X2X4" BRISTLE W/RED HDL | crack injection | Daily
| Target- Aquaplug 50 lb pail | crack injection | Daily
| Xypex patch and plug- 50 lb | crack injection | Daily
| Xypex concentrate 50 lb | crack injection | Daily
| hydrocloric acid 31.45 % 4l | crack injection | Daily
| Load CFI / XPS panels per job | Insulation | Daily
| PL glue, fasteners & drill bits loaded | Insulation | Daily
| test shot blater | Traffic Coatings | Daily
| confirm ventallation is in place | Traffic Coatings | Daily
| confirm power is on site and ready to go | Traffic Coatings | Daily
| test Hermanator vacum | Traffic Coatings | Daily
| test DG 150 grinder | Traffic Coatings | Daily
| Xylene soak squeege frames, inserts and roller frames | Traffic Coatings | Daily
| clean vacum filters | Traffic Coatings | Daily
| Sasuages of Dymonic 100 | Traffic Coatings | Daily
| Material - ADD DETAIL | Traffic Coatings | Daily
| Equipment - ADD DETAIL | Traffic Coatings | Daily
| coating sand | Traffic Coatings | Daily
| spike cleats loaded | Traffic Coatings | Daily
| test caulking guns | Waterproofing | Daily
| Fill jerry cans for boom lift | Waterproofing | Daily
| impact driver drill charged | Waterproofing | Daily
| 3 barrels of Tremco TP 260 loaded | Waterproofing | Daily
| fire up spray machine and test pressure and that it sprays | Waterproofing | Daily
| fire up calcium pump and test pressure to 3000 | Waterproofing | Daily
| Pump emergeny repair kit loaded | Waterproofing | Daily
| brush off and clean dirt and dust from floor walls and machines | Waterproofing | Daily
| Actuator | Waterproofing | Daily
| Actuator lube | Waterproofing | Daily
| Actuator repair bag | Waterproofing | Daily
| tar gun taken apart and cleaned | Waterproofing | Daily
| tar gun stored in diesel bucket overnight | Waterproofing | Daily
| extra spray gun tips | Waterproofing | Daily
| fill calcium choride container | Waterproofing | Daily
| spray suits | Waterproofing | Daily
| spray hoods | Waterproofing | Daily
| P 100 gas pucks | Waterproofing | Daily
| fender washers mimum 200 | Waterproofing | Daily
| 1/12 actuator pins mimum 200 units | Waterproofing | Daily
| yellow shot mimum 200 units | Waterproofing | Daily
| anle grinder | Waterproofing | Daily
| angle grinder battery charged | Waterproofing | Daily
| Material - ADD DETAIL | Waterproofing | Daily
| Equipment - ADD DETAIL | Waterproofing | Daily
| Load membranes & primers per job list | Waterproofing | Daily
| Secure Tremproof barrels / Vulkem pails | Waterproofing | Daily
| Torch, propane & rollers loaded | Waterproofing | Daily
| test actuator | XPS | Daily
| Test ramset | XPS | Daily
| ramset gas cartridges | XPS | Daily
| ramset gun | XPS | Daily
| Greyco Acid flush pump | Crack Injection | Daily
| load in picture confirmed | Always on Vehicle | Daily
| tube of green monster | Always on Vehicle | Daily
| hard hats | Always on Vehicle | Daily
| tar whip hose loaded | Waterproofing | Daily
| 4 caulking slicks | Waterproofing | Daily
| saftey glasses | Always on Vehicle | Daily
| Milwakee Leaf blower | Always on Vehicle | Daily
| Barricade caution tape | Always on Vehicle | Daily
| most senior employee to complete the days work order on route ot the shop | Always on Vehicle | Daily
| Log into builder trend and start time clock for assigned site | Always on Vehicle | Daily
| Text site contact when leaving shop to advise on ETA | Always on Vehicle | Daily
| clear poly 10 x 100 | Always on Vehicle | Daily
| 1 box of nitrile gloves | Always on Vehicle | Daily
| Milwakee packout loaded with (hammer,tape measure, wrenches, chissel, vice grip pliers) | Always on Vehicle | Daily
| bag of rags | Always on Vehicle | Daily
| wet tools set out to dry and not stored in cases | Always on Vehicle | Daily
| contractor garbage bags | Always on Vehicle | Daily
| broom | Always on Vehicle | Daily
| 4 paint brushes | Always on Vehicle | Daily
Daily